# Architectural Proposal — Standardized Apartment Building & Cost Analysis

## Author

Oscar (Lead Architect, Awesome Inc.)

## Executive summary

This document presents a detailed architectural and cost-feasibility proposal for a standardized apartment building product that Awesome Inc. can offer to clients as a pre-defined, configurable building type. The proposal expands the concept from a high-level outline into a comprehensive package that includes:

- A refined design concept and spatial strategy emphasizing functionality, durability and energy efficiency.

- A detailed representative unit mix, area schedule and illustrative unit descriptions.

- Standard elements, tiered options and a fully expanded specification matrix for procurement.

- Structural, MEP and sustainability targets with suggested performance criteria and typical component selections.

- A more detailed preliminary cost model with line-item breakdowns, sensitivity scenarios and lifecycle (operational cost) indications.

- A procurement and delivery strategy with recommended contract forms, quality assurance measures and a risk register.

- A phased project timeline with delivery milestones, decision points and responsibilities.

- Next-step actions, deliverables and practical checklists for moving to pre-tender and tender stages.

Numbers included are conceptual early-stage estimates intended to establish feasibility and guide decisions. Typical expected accuracy at this stage: +/- 10–15%. These should be refined by site-specific investigations and a cost consultant prior to tender.

## Project objectives (expanded)

Primary objectives - Deliver a repeatable, high-quality apartment typology clients can select with minimal bespoke design time, enabling rapid deployment across multiple sites. - Prioritize durability, low operational energy demand and straightforward maintainability to reduce lifecycle costs and enhance marketability. - Maintain a modular palette of materials and finishes with a limited number of configurable options to accelerate procurement and control cost variability. - Ensure basic compliance with applicable German residential regulations and accessibility standards, with the understanding that local authority requirements will be confirmed at permit stage.

Secondary objectives - Reduce embodied carbon where cost-effective by offering a timber-concrete hybrid upper floor option and specifying low-carbon materials. - Achieve a balance between initial capital cost and lifecycle operating cost—promote investments in fabric and systems that reduce tenant energy costs. - Create a product that can be marketed to mid-market buyers and long-term renters, with optional premium finishes packages for PRS (Private Rented Sector) or for-sale units.

Success criteria - Cost: Achieve competitive installed cost per m2 within the ranges identified in the preliminary estimates. - Performance: Target operational heating demand ≤ 45–60 kWh/m2·a (illustrative, depending on final envelope and system choices) and balanced ventilation with heat recovery. - Accessibility: At least one fully wheelchair-accessible unit on the ground floor and accessible common entries. - Delivery: Design development to 60% and permitting milestones met within the projected schedule (see Milestones section).

## Key assumptions (explicit, expanded)

- Gross floor area (GFA): 1,200 m2 (typical 3–4 storey mid-rise building). This GFA includes grossed circulation and common areas.

- Net lettable/sale area (NLA): typically ~72–78% of GFA depending on corridor, core and plant room area. For our representative mix NLA ~880–940 m2.

- Unit count: 12 units (example mix specified below). Unit mix and sizes can be adjusted by the client.

- Typical floor to floor height: 2.7–3.0 m depending on mechanical stacking requirements and local planning height allowances.

- Service cores: single central stair and lift core serving all floors; location assumes long-side access corridor to maximize cross-ventilation where possible.

- Target market: German mid-market buyers or long-term renters. Fit-out standards oriented to “mid-range” finishes as base-case; premium tier available.

- Geotechnical, utility connection and planning constraints: unknown at this stage; may materially affect foundation cost, basement vs slab-on-grade decisions and external works.

- Cost basis: prices in EUR and are net unless specified; VAT assumed at 19% for final totals. Excludes land acquisition, major off-site infrastructure, demolition or remediation costs unless stated.

- Time and market: cost estimates are early-stage and subject to commodity price volatility, labour availability and regional market differences.

- Energy and carbon: operational energy figures are illustrative target values; final performance will require detailed energy modelling.

## Design concept (expanded)

Design philosophy - A clean modernist volume with simple roof geometry (either a shallow pitched roof or a shallow flat roof with parapet and single-plane slope) to reduce construction complexity and roof detailing costs. - Compact circulation: minimize wasted corridor area through efficient stacking and core placement. Target gross-to-net efficiency (NLA/GFA) of ~0.75–0.80. - Cross-ventilated and well-daylit units where the site orientation allows. Primary living spaces face south or east-west wherever possible. - Private outdoor space: balconies or loggias for primary living rooms on two-bedroom and three-bedroom units. Balcony depth typical 1.4m for usability, balustrade minimum 1.1m height. - Durable façade: prefabricated insulated panels or ventilated rainscreen with fibre-cement or composite panels to optimize construction speed and reduce on-site labour. - Standardized service modules (kitchens/bathrooms) for procurement and repeatability; bathroom pod option for faster fit-out and predictable MEP interfaces. - Simple, legible structural grid (e.g., 6.0m x 4.5m or similar) that supports flexible internal partitions and maximizes repeatability of unit layouts.

Spatial strategy (typical floor) - Ground floor: accessible entry lobby, mail/parcel room, plant room, bike store and one accessible flat (or adaptable unit), utilities and waste collection area. Small external amenity (private or shared courtyard). - Upper floors: mix of 1-, 2- and 3-bedroom flats arranged around a central corridor/stair core. Max unit depth targeted ~8–9m to ensure daylight to living spaces. - Circulation: single stair + lift providing evacuation and accessibility; stair designed to meet local fire egress standards (with half-landing widths and handrails according to DIN guidance). - Vertical services: central riser zone close to the core for stacked plumbing and ventilation runs; electrical distribution designed for individual apartment metering.

Aesthetic intent - Simple volume with restrained detailing; balconies as subtle horizontal elements for composition. - Material palette: neutral mineral render or timber composite panels as accents; anodized aluminum window frames in muted tones. Emphasis on low-maintenance finishes.

## Typical unit mix (example) — expanded schedule

| Unit type | Count | Typical net area (m2) | Typical gross area (including common) (m2) | Comments | |---:|---:|---:|---:|---| | 1-bedroom (1BR) | 4 | 42–48 | 65–72 | Open-plan kitchen/living, 1 bathroom, balcony or juliet on select units | | 2-bedroom (2BR) | 6 | 60–75 | 85–95 | Living/dining with balcony, 1 bathroom + 1 ensuite optional depending on layout | | 3-bedroom (3BR) | 2 | 88–95 | 115–125 | Larger living space, family bathroom and ensuite, full balcony or terrace |

- Example area totals: Net sale/let area ~920 m2; Project GFA including circulation, plant, walls, and external envelope ~1,200 m2.

- Unit planning notes: All 2BR designed for at least one double-aspect where possible; 3BR positioned to maximize cross-ventilation and daylight.

Representative unit descriptive sketches (textual) - 1BR (approx. 45 m2): Entry hall (2.5 m2) with storage, open-plan living/kitchen (23 m2) with direct access to a balcony (4.5 m2), bedroom (11 m2), bathroom (4.5 m2). Kitchen module 2.4m linear with space for full-height fridge and integrated dishwasher. - 2BR (approx. 68 m2): Entry with coat/storage cupboard, living/dining (28 m2) with balcony (6 m2), kitchen (separated or galley), bedroom 1 (13 m2) with wardrobe, bedroom 2 (10 m2), bathroom (6.5 m2) with washer-dryer provision. Consider layout variants with ensuite to master depending on client requirement. - 3BR (approx. 92 m2): Entrance lobby with built-in storage, kitchen/dining (16 m2) semi-open to living room (26 m2), balcony or loggia (8–10 m2), master bedroom (15 m2) ensuite (4.5 m2), two additional bedrooms 10 & 9 m2, family bathroom 6.5 m2.

## Standard elements & options catalogue (expanded)

This section provides a standardized element catalogue for structural, envelope, internal finishes and systems. For procurement, elements are grouped into Base (Value), Standard (Base-case), and Premium (Up-sell) tiers.

- Structural systems

- Option A — Reinforced concrete frame (Base-case)

  - Cast-in-place RC slabs and beams, reinforced columns. Standard slab thickness: 200–220 mm for solid slabs; flat slab or ribbed slab options depending on span.

  - Strengths: robust, familiar to local contractors, good fire resistance.

  - Considerations: higher embodied carbon and longer wet trades duration.

- Option B — Timber-concrete hybrid (Value & Sustainability option)

  - CLT or glulam for floors and upper walls with thin concrete topping for acoustic and service runs.

  - Strengths: reduced embodied carbon, faster erection, lighter foundations.

  - Considerations: acoustic detailing, fire treatment and local contractor capability.

- Façade systems

- Base: Insulated mineral render over breathable insulation board on a masonry backup or insulated prefabricated panel.

- Standard: Prefabricated insulated rainscreen panels with fibre-cement outer boards (concealed fixings). Thermal spacer details to minimize thermal bridging.

- Premium: Prefinished metal or natural timber rainscreen accents with higher-grade fastenings and integrated LED lighting features for balcony soffits.

- Windows & external doors

- Base: PVC triple-glazed units Uwindow ≈ 1.2 W/m2K (budget), standard high-performance: aluminum-clad timber or thermally-broken aluminum with triple glazing Uwindow ≈ 0.9–1.0 W/m2K.

- Thermal breaks and continuous perimeter seals mandatory. Limiting solar gain via externally mounted shading where required.

- Kitchens & bathrooms (module approach)

- Three-tier finishes: Basic, Standard, Premium.

- Standard module sizes: 2.4m, 3.0m and 3.6m linear kitchens; bathroom pods typical 2.2m x 2.4m module for 1BR/2BR.

- Plumbing manifolds and stacking to be coordinated with service riser locations.

- HVAC & ventilation

- Mechanical ventilation with heat recovery (MVHR) by default for energy efficiency; efficiency target sensible heat recovery >75% in standard model, >85% in premium.

- Heating/hot water: Building-level heat pump (air-source) with plate heat exchangers to apartment distribution, or individual heat-pump-at-apartment as a lower-cost distributed option.

- Domestic hot water: centralized instantaneously sized heat pump or buffer storage depending on tenant demand profile.

- Optional: GSHP (ground-source heat pump) where ground conditions favourable and CAPEX can be justified.

- Renewable energy

- PV-ready roof with structural allowance for arrays: roof area allowance to mount up to 30–50 kWp depending on area and orientation (typical 15–25 m2 per kWp required depending on module efficiency and tilt).

- Battery storage optional for common-area backup and load-shifting.

- Accessibility & fire safety

- Minimum 1 wheelchair-accessible unit (ground-floor or lift-served), accessible main entry route, door widths min 0.9 m, corridor width min 1.2 m in accessible routes.

- Fire-safety systems to meet local code: smoke detection, emergency lighting and fire-separating construction as required.

- Internal finishes (example)

- Floors: vinyl plank in wet areas (basic), engineered timber or high-grade LVT in living (standard), solid wood or premium LVT (premium).

- Walls: washable paint (standard), porcelain tiles in bathrooms up to 2.2 m (standard), full-height tiles or natural stone (premium).

- Joinery: flat-pack or built-in wardrobes tuned to tier.

- Landscape & external works

- Base: permeable paving, basic tree planting and minimal levels modification.

- Standard: designed planting beds, seating, communal amenity path, secure bike parking for 1.5–2 bikes per unit.

- Premium: landscaped courtyard with seasonal planting, rain gardens and individual garden plots for ground-floor units.

## Sustainability & energy strategy (expanded)

Overall approach - Fabric-first philosophy: prioritize insulation and airtightness to reduce heating demand and system size. Target airtightness n50 = 1.0–1.5 h^-1 for base-case, 0.6–1.0 h^-1 for premium. - Building Envelope Target U-values (indicative targets for mid-market, adjust for local code): - External walls: 0.18–0.20 W/m2K (standard); 0.12–0.15 W/m2K (premium) - Roof: 0.12–0.15 W/m2K - Ground slab: 0.15–0.20 W/m2K with edge insulation - Windows (triple-glazed): 0.9–1.1 W/m2K - Mechanical ventilation with heat recovery (MVHR) to ensure fresh air and reduce heating loads. Target system COP equivalent for heat pumps > 3.0 (seasonal performance factor SPFs 2.5–3.5 depending on system). - Heat pump technology: air-source heat pumps as standard; ground-source (vertical or horizontal) as premium option if ground conditions and budget permit. - Solar PV: size arrays to offset common area and some tenant electricity usage where feasible; integrate with tenant billing and potential for feed-in revenue where permitted. - Embodied carbon considerations: assess timber-concrete hybrid option vs full reinforced concrete in a life-cycle analysis (LCA) during design development.

Performance targets (illustrative) - Space heating demand: aim for 40–60 kWh/m2·a (representative depending on final envelope), or better with premium insulation. - Primary energy demand: design to meet GEG requirements; coordinate with energy consultant for exact targets and local compliance pathways.

Operational benefits - Lower utility costs for tenants, which is attractive for PRS and for-sale markets. - Potential for sustainability certification (e.g., DGNB or equivalent) if client chooses the premium path.

## Compliance & accessibility (expanded)

Regulatory references and process - High level: Compliance with German national and local building regulations is required. At minimum, the design will be checked against: - Gebäudeenergiegesetz (GEG) — energy performance. - DIN standards covering accessibility and planning (e.g., DIN 18040 for barrier-free building) — verify version/current standards in each local authority. - Local fire safety requirements, which may reference Musterbauordnung (MBO) and local fire authority amendments. - Local planning and zoning rules: setbacks, height limits, parking provisions and landscaping requirements. - Accessibility: one fully accessible/visitable apartment recommended on ground floor or lift-served floor with step-free access to entrances and common amenity spaces. Typical accessibility checklist: - Entry threshold: step-free and level (max crossfall 1:50). - Door clear width: 900 mm minimum for accessible doors. - Turning circle in living/kitchen or bedroom: 1500 mm diameter. - Bathroom: clear maneuvering space and reinforced walls for potential grab rails. - Lift: internal dimensions 1100 x 1400 mm (or as required by local standards) to allow stretcher access where required.

## Structural and MEP outline (early-stage, expanded)

Structural outline - Grid and spans: adopt a regular grid (e.g., 6.0m x 4.5m) enabling simple panel dimensions and repeatable floor plates. Minimize non-repetitive elements to reduce carpenter and formwork complexity. - Foundations: shallow strip or pad foundations assumed for competent ground; piled foundations to be budgeted as a risk if poor soils are found. - Lateral stability: shear walls or diaphragms as required; coordinate with structural engineer for seismic or wind load requirements if needed.

MEP outline - Central plant room sized for heat-pump, MVHR unit, DHW tanks and electrical distribution. Allow for future PV inverter location. - Hot water distribution: insulated manifold system for each apartment or centralized DHW with circulated loops depending on design choice and energy efficiency cost trade-offs. - Electrical: individual apartment metering; consider pre-wiring for EV chargers in allocated bike/parking areas. - Data & comms: provision for high-speed data backbone and shared Wi-Fi in common areas; pre-wire living spaces for flexible tenant need. - Acoustic: floor build-ups and separating wall partitions designed to meet local sound insulation requirements (R’w 50–55dB airborne; impact sound reduction L’nT,w to meet Code). Increased acoustic performance in premium or where local requirements exceed typical.

## Preliminary cost estimate (base-case and value-engineered alternative) — expanded

Refined assumptions: GFA 1,200 m2; 12 units; Base-case mid-range finishes. All costs exclusive of land acquisition.

A. Base-case (mid-range finishes) — detailed breakdown - Construction cost (building shell + interior fit-out + services): 1,200 m2 x €2,400/m2 = €2,880,000 - Shell & structure: 45% = €1,296,000 - Interior fit-out & finishes: 20% = €576,000 - Building services (HVAC, electrical, plumbing): 18% = €518,400 - Other works included in construction cost (balconies, windows, doors, internal partitions, stair and lift): included above - External works & landscaping: €150,000 - Professional fees (architect, structural, MEP, permit, specialists): 10% of construction cost = €288,000 - Permits and statutory fees (included within professional or as separate allowance): €50,000 (allowance, site dependent) - Contingency (7% of construction + external works): 0.07 x (€2,880,000 + €150,000) = €212,100 - Subtotal before VAT: €3,538,100 (inc. permit allowance) - VAT (19%): €672,238 - Total (incl. VAT): €4,210,338 - Approx. total incl VAT per m2 (GFA): €3,509/m2 - Per-unit cost (12 units): approx. €350,861 per unit (incl. VAT)

Notes: - Slight differences from previous totals due to added permit allowance and rounding. - Construction cost per m2 includes core & shell, fit-out and services as noted.

B. Value-engineered scenario (cost focus) - Construction cost: 1,200 m2 x €2,000/m2 = €2,400,000 - Adjusted percentages reflecting lower-spec finishes and simpler façade - External works & landscaping: €120,000 - Professional fees (10% of construction cost): €240,000 - Permits and statutory fees allowance: €40,000 - Contingency (7%): 0.07 x (€2,400,000 + €120,000) = €176,400 - Subtotal before VAT: €2,876,400 - VAT (19%): €546,516 - Total (incl. VAT): €3,422,916 - Approx. per m2 (GFA): €2,856/m2 - Per-unit cost: approx. €285,243 per unit (incl. VAT)

C. Sensitivity and escalation allowance - Market volatility: Include an escalation allowance of 3–6% if tender expected beyond 6–9 months. - Commodity risk: If steel or timber prices increase by 10% this could add ~2–3% to construction cost depending on structural choice.

D. Cost breakdown table (base-case illustrative)

| Category | % of construction | € (approx) | |---|---:|---:| | Shell & structure | 45% | 1,296,000 | | Interior fit-out & finishes | 20% | 576,000 | | Building services (HVAC, electrical, plumbing) | 18% | 518,400 | | External works & landscaping | 4% | 150,000 | | Professional fees & permits | 8% | 338,000 (including permit allowance) | | Contingency & allowances | 5% | 212,100 | | Subtotal (before VAT) | 100% | 3,090,500* | | VAT (19%) | | 587,195 | | Total incl VAT | | 3,677,695 |

*NOTE: Table illustrative — see A above for the full reconciliation.

E. Lifecycle cost (LCC) note (operational savings illustration) - If the premium envelope reduces heating demand by 20 kWh/m2·a relative to base-case (e.g., from 60 to 40 kWh/m2·a), for a typical energy price of €0.12/kWh this equates to ~€2,880/year saved across all units (1,200 m2 × 20 kWh × €0.12). Over a 25-year period (discounting not applied here), the operational savings become material and can justify additional upfront investment depending on financing and occupant type.

## Cost breakdown by category (approximate split, base-case) — expanded and reconciled

- Shell & structure: 45% (~€1,296,000)

- Foundations, structural frame, roof, external envelope

- Interior fit-out & finishes: 20% (~€576,000)

- Floors, bathrooms, kitchens, doors, built-in joinery

- Building services (HVAC, electrical, plumbing): 18% (~€518,400)

- MVHR, heat pump, hot water plant, apartment distribution, EV/lighting allowances

- External works & landscaping: 4% (~€150,000)

- Paving, planting, bike store, boundary treatments

- Professional fees & permits: 8% (~€288,000)

- Architect, structural, MEP, QS, specialist surveys allowances

- Contingency and allowances: 5% (~€212,100)

- Unforeseen site conditions, minor scope adjustments

These splits are indicative and will be updated after tender returns.

## Value-engineering opportunities (detailed)

Primary cost reduction strategies (to achieve value-engineered scenario or better) 1. Façade simplification - Replace premium rainscreen panels with a more standard insulated render system or simple fibre-cement rainscreen without bespoke details. Savings: up to 6–10% of façade cost depending on scope. 2. Standardized modules - Use repeated kitchen and bathroom pod dimensions across units to reduce bespoke joinery and plumbing variations. Savings: 3–6% on fit-out. 3. Windows optimization - Use thermally-broken aluminum with double or lower-spec triple glazing balancing U-value and cost; tune solar gain via shading. Savings: 2–4% of total building cost. 4. Structural efficiency - Optimize grid and beam sizes, reduce cantilevers and bespoke transfer beams. Savings: 2–5% of structural cost. 5. Procurement route - Tender as design-and-build or select a contractor via partner frameworks to capture contractor efficiencies and price certainty. Potential to reduce overall cost and reduce contingency needs. 6. Reduce change orders - Early coordination of services, avoid late client-driven finish changes, and standardize selections to minimize variations during construction.

Trade-offs - Lower initial CAPEX may increase operational costs, reduce market appeal for eco-conscious buyers and increase future retrofit costs. Value-engineering must be balanced against lifecycle and market objectives.

## Procurement & contract strategy (expanded)

Options 1. Traditional design–bid–build (DBB) - Pros: Clear separation of design and construction, typically good design control. - Cons: Contractor pricing risk; slower and may result in higher cost contingency. - Recommended when design clarity and control is paramount.

- Design-and-build (D&B) / Contractor-led

- Pros: Single point responsibility, potential cost and programme certainty, contractor innovation on buildability.

- Cons: Reduced design control; requires robust employer’s requirements and careful tender documents.

- Recommended for repeatable product where time-to-market and cost certainty are priorities.

- Early contractor involvement (ECI) or alliancing

- Pros: Collaborative risk-sharing, early cost input, better constructability integration.

- Cons: Complex contract arrangements and potential cost for advisor management.

Contract forms to consider: FIDIC-lite, German VOB-based D&B contract or bespoke forms depending on procurement jurisdiction and client preferences.

Payment milestones (typical) - Mobilization: 5% on contract signing - Foundations completed: 15% - Superstructure topped out: 30% - External envelope watertight: 20% - Practical completion: 25% (less retention) - Retention: 3–5% released following defects period

Tendering duration: Allow 4–6 weeks for tender issue + 4–6 weeks for evaluation and appointment.

## Risks & contingencies (expanded with matrix)

Top project risks (high-level risk matrix with mitigation strategies):

- Site unknowns (geotechnical) — High

- Impact: Foundation redesign, increased cost and programme delays.

- Mitigation: Commission early geotechnical survey; include scope for piled foundations in initial budget as allowance.

- Market price volatility — Medium–High

- Impact: Increases to material and labour costs.

- Mitigation: Consider early procurement packages, fixed-price subcontractor bundles, and contract escalation clauses.

- Permit & planning delays — Medium

- Impact: Programme delay and cost escalation.

- Mitigation: Early pre-application engagement with planning authority, use of model images and massing studies for quick feedback.

- MEP complexity & stacking issues — Medium

- Impact: Rework to ceiling/floor distribution and increased costs.

- Mitigation: Early MEP coordination, standardized riser locations and compact plant room design.

- Contractor capacity / labour shortages — Medium

- Impact: Extended programme, higher cost.

- Mitigation: Tender to multiple contractors, include local/regional contractors in tender list, consider phased delivery.

- Acoustic/fire requirements beyond standard — Low–Medium

- Impact: Increased wall/floor build-up cost and potential redesign.

- Mitigation: Confirm statutory requirements early and design to exceed minimum where possible to avoid later retrofit.

Contingency recommendation - Base-case: 7–10% contingency recommended at early stage; reduce after 60% design and fixed-price tender. - Value-engineered scenario: still carry 5–7% contingency to provide buffer against world commodity movement and site surprises.

## Project milestones & indicative durations (expanded with schedule and decision points)

| Phase | Key activities | Indicative duration | Decision points / deliverables | |---|---|---:|---| | Brief & feasibility | Confirm brief, site appraisal, geotech, utility checks | 2–4 weeks | Confirm GFA, unit mix, target cost | | Concept design | Massing, unit layouts, initial technical strategy | 6–8 weeks | Sign-off concept; update cost model | | Design development (to 60%) | Coordination with structural & MEP; detailed envelope strategy | 8 weeks | 60% design pack, updated QS estimate | | Permit preparation & submission | Prepare working drawings for permit; specialist reports | 8–12 weeks (authority dependent) | Permit submission | | Procurement strategy | Tender pack development, contractor prequalification | 4–6 weeks | Issue tender or select D&B partner | | Tender period & award | Tender evaluation & negotiation | 6 weeks | Contractor appointment | | Construction | Site set-up, foundations, superstructure, fit-out | Approx. 40–48 weeks | Monthly progress reporting & milestone payments | | Commissioning & handover | Systems commissioning, snagging, handover documentation | 4–6 weeks | Practical completion & certificate | | Defects liability period | Post-handover rectification period (12 months) | 12 months | Final account & defects closeout |

Total indicative time from brief confirmation to practical completion: approximately 14–22 months depending on permitting and procurement route.

## QA/QC, testing and commissioning (expanded)

Quality assurance measures - Design reviews at key stages: Concept, 30%, 60%, 90% with clubbed QS reviews to manage cost. - Peer review for structural and fire strategy. - Factory inspection for prefabricated façade panels and bathroom pods. - MEP pre-installation coordination meeting to check stacking, access and commissioning sequences.

Testing and commissioning - Envelope air-tightness testing (blower door) — target n50 per design stage. - Thermal imaging and inspections at practical completion to check insulation continuity. - MVHR commissioning and balancing certificates. - Heat pump and DHW plant commissioning per manufacturer instructions with water treatment records. - Electrical testing and PAT testing for all equipment. - Final handover pack to include O&M manuals, as-built drawings, warranties and guarantees.

## Deliverables I can produce next (expanded)

If commissioned, Awesome Inc. (Oscar) can provide: - Refined cost estimate tied to an agreed unit mix and exact GFA including sensitivity analysis for different structural choices. - A set of standard plan sketches (2D) and a simple 3D massing study in SketchUp for early marketing and planning pre-application. - Model specifications (spec sheets) for the following building elements: - Kitchen module (basic/standard/premium) - Bathroom pod (typical dimensions and fittings) - Façade panel detail (standard vs premium) - Window schedule and thermal performance table - A permit submission package outline and a tailored procurement strategy with recommended contract wording and tender documents. - Lifecycle cost comparison showing payback on improved envelope and PV investment across 10–30 years (presenting basic net-present-value assumptions on request).

## Closing recommendations (expanded)

Short-term (immediate next steps) 1. Confirm the brief: finalize GFA, unit mix and target finish level. Owner: John (Project Sponsor) & Oscar (Lead Architect). Deadline: 2 weeks. 2. Commission site due diligence: Geotechnical ground investigation, topographical survey and utility mapping. Owner: Awesome Inc. (Procurement). Recommend commission within 4 weeks to avoid programme delay. 3. Appoint a cost consultant / quantity surveyor to produce a pre-tender estimate and update the target cost. Owner: John / Cost Consultant. Allow 2–4 weeks. 4. Stakeholder engagement: early meeting with planning authority and local fire brigade where required to test the concept. Owner: Oscar with John. Allow 2–3 weeks.

Medium-term 5. Design development to 60% including full coordination with structural and MEP engineers. Owner: Oscar (Lead Architect) with Richard (structural liaison) and MEP partner. 6. Prepare permit submission and run parallel procurement plan (consider ECI or D&B depending on client appetite). 7. Complete energy modelling for GEG compliance and to finalise MVHR/heat pump sizing and PV sizing.

Long-term 8. Tender and appoint contractor with clear instructions about standardization and product repeatability to maintain margins. 9. Monitor one or two first projects closely to refine the standard product, procurement lead times and installation quality.

If you want, I can now: 1) Adjust the model to a different GFA or unit count (e.g., 16 units at 1,500 m2 or 8 units at 900 m2) and update costs and schedule immediately. 2) Produce a simple SketchUp massing file and a set of standard 2D plans (ground + typical floor + roof) for marketing and pre-application. 3) Prepare a one-page client brochure summarizing the offering with key selling points, costs and images for sales.

Please state which option you prefer and any specific changes to assumptions (GFA, targeted finishes, sustainability target or procurement route). I will deliver the selected follow-up product and an updated detailed cost sheet or sketch package.

Appendices

Appendix A — Example detailed unit area schedule (full) - Ground floor - Lobby & entry: 18 m2 - Plant room: 16 m2 - Accessible unit 1BR: gross 70 m2 (net 45 m2) - Bike & bin store: 22 m2 - External terrace (shared): 30 m2 - Typical upper floor (each) - 1BR x1: gross 68 m2 - 2BR x2: gross 92–95 m2 each - Circulation & core allowance per floor: 12–15% of floor plate

Appendix B — Indicative specification table (summary)

| Item | Base | Standard | Premium | |---|---|---|---| | Windows | PVC triple-glazed U≈1.2 | Aluminum-clad timber triple U≈1.0 | Thermally-broken aluminum U≤0.9 | | Roof | Insulated single-ply membrane | Cold roof with insulation & parapet | Green or PV-integrated roof | | Façade | Render over insulation | Rainscreen fiber-cement panels | Timber/metal high-end rainscreen | | Ventilation | Extract-only with trickle vents | MVHR 75% recovery | MVHR 85% recovery with smart controls | | Heating | Electric DHW + space heaters | Building heat pump + MVHR | GSHP + PV + battery |

Appendix C — Contact & roles (suggested) - Project Sponsor: John (Owner) - Lead Architect: Oscar (Awesome Inc.) - Structural Liaison: Richard (internal/consultant) - MEP Partner: To be appointed (recommend early ECI) - Cost Consultant: To be appointed externally for pre-tender and tender checks - Procurement Lead: Awesome Inc. Procurement team

End of document.