# Executive summary

Wild Advice Partners recommends a phased, procurement-friendly approach to deliver FEMA-eligible Phase 1 emergency kits quickly, while preserving a funded upgrade path for Phase 2. The objective is to balance speed (to meet urgent operational timelines and NGO bridge-funding windows) with strict compliance to FEMA eligibility rules, auditable QA evidence, and a clear contractual path for subsequent upgrades.

Key recommendations - Use a single RFQ/SOW that requires vendor submission of two-option bids: (A) Emergency Minimal / FEMA-critical Phase 1 and (B) Standard / full-spec Phase 2. Bidders must supply fixed upgrade pricing and committed timelines for Phase 2. - Enforce FEMA eligibility by mandating the one-page FEMA_nonnegotiables_Lisa.pdf as the compliance baseline, and require acceptance evidence (photos, invoices, test results) at delivery for FEMA reimbursement. - Run parallel tracks: a rapid analytics/compliance review (Lisa Carter) and an RFQ/contracting track (Oscar & Procurement). Secure NGO conditional MOU for bridge funding in parallel to reduce funding risk. - Use holdback/performance-bond mechanics (contract language provided below) to preserve incentive and cashflow for Phase 2 upgrades.

This report provides: a detailed implementation timeline, owners, step-by-step immediate actions for the next 0–48 hours, expanded procurement and RFQ/SOW language, evaluation criteria and matrix examples, QA and FEMA documentation requirements, a risk register with mitigation measures, deliverables table, a communication plan, and recommended next steps to move to award.

## Background (expanded)

Situation summary - There is an urgent operational need to procure emergency kits that must be FEMA-eligible for reimbursement. The program has two logical stages: - Phase 1: Emergency Minimal — the minimum set of items and specifications required for FEMA eligibility and immediate deployment. - Phase 2: Standard / Full-spec — optional upgrades or additions that improve durability, user experience, or lifecycle, but which are not strictly required for FEMA reimbursement. - Time is critical. Procurement delays risk: - Missing response windows for field operations. - Losing access to NGO bridge funding earmarked to cover Phase 2 upgrades. - Reduced vendor capacity or price increases if award is delayed.

Constraints and assumptions - Vendors can prepare two-option proposals within 24–36 hours of a clarified RFQ. - NGO partners can deliver a conditional MOU (to support Phase 2 funding) on a short timeline. - Procurement/legal will accept a phased-award approach or explicit contract holdback that preserves upgrade mechanics. - FEMA_nonnegotiables_Lisa.pdf is treated as mandatory baseline for Phase 1 compliance. Vendors must explicitly map line-items to that checklist.

Operational goal - Award and deliver Phase 1 kits within the operational window (target: shipment initiation within 2 weeks of award), with documented acceptance evidence to support FEMA reimbursement claims. - Secure contract terms and funding path for Phase 2 so upgrades can be ordered and delivered on a known schedule with fixed costs.

## Recommended approach (expanded and detailed)

Overview 1. Phased competitive award - Require two-option bids: Emergency Minimal (Phase 1) and Standard (Phase 2). Bidders must include: - Bill of Materials (BOM) with line-item-level mapping to FEMA line-items. - Fixed upgrade pricing for converting Phase 1 to Phase 2 per kit or per unit batch. - Firm timelines for Phase 1 delivery and Phase 2 upgrade completion (where upgrade may be shipped separately or built-in to initial order). - Rationale: This keeps the procurement competitive, shortens time-to-delivery for FEMA-eligible content, and provides financial clarity for funding the upgrades.

- Protect FEMA eligibility

- Make FEMA_nonnegotiables_Lisa.pdf an attachment to the RFQ and a mandatory compliance checklist.

- Require vendors to provide physical evidence (photos, certificates, test reports) tied to line-items at acceptance to ensure allowable FEMA reimbursement.

- Prioritize anchoring/structural supports, specified materials/tests, and documented acceptance evidence in both evaluation and contractual terms.

- Parallel tracks

- Rapid analytics/compliance track (owner: Lisa Carter) to review rebids quickly and flag non-compliance within ~4 hours during working hours; deeper 24-hour pass if required.

- RFQ/contracting track (owner: Oscar + Procurement) to issue RFQ amendments, manage clarifications, and finalize contract language including holdback/performance bond.

- Funding track: NGO to post a conditional MOU that defines amount, triggers, permitted uses (limited to Phase 2 upgrades), timing, and basic legal guardrails.

Detailed procurement structure - Evaluation should use a two-stage scoring matrix: 1. Mandatory pass/fail compliance to FEMA_nonnegotiables (any failure = disqualification for Phase 1 award). 2. Weighted scoring for price, lead time, upgrade price fixedness, vendor capacity, QA plan, and warranty terms. - Award Phase 1 to the most compliant and responsive vendor that meets FEMA non-negotiables and offers acceptable upgrade pricing & timelines. - Retain an explicit contractual holdback (recommended 15–30% of Phase 1 value) pending completion of Phase 2 upgrades or submission of upgrade-related deliverables per contract. Alternatively, use an approved performance bond.

Contract mechanics for upgrades - Include an upgrade option clause with: - Fixed unit upgrade price or formula. - Guaranteed timeline for upgrade conversion or separate Phase 2 shipments. - Remedy clause if vendor fails to perform (e.g., liquidated damages, replacement, or retention of funds for third-party completion). - Keep Phase 1 acceptance independent of Phase 2 upgrade approval for speed, but condition release of holdback/final payment on successful proof-of-upgrade (if NGO funds will be used to support that release).

## Immediate actions (0–48 hours) — enhanced checklist and sample text

Critical next 48-hour checklist (owner and measurable outputs) - Oscar (Lead, RFQ/SOW) - Action: Upload RFQ/SOW amendment to shared folder; send a notification to distribution list; CC Lisa. - Deliverable: RFQ Amendment v1 (PDF + editable DOCX) within 12 hours. - Contents to include: - Phase 1 mapped to FEMA line-items. - Phase 2 optional upgrades with fixed upgrade prices/timelines. - Acceptance/QA criteria and required evidence types and formats. - Milestone payments, holdback percentage, and suggested performance-bond language. - Sample notification subject: “RFQ Amendment v1 — Phase 1 FEMA Mapping & Phase 2 Upgrade Options — Action Needed”

- Marcos (Bid clarifications)

- Action: Post bidder clarifications; log all vendor Q&A in a master clarifications log.

- Deliverable: Clarifications Log v1, within 12 hours of RFQ amendment.

- Include: Which line-items were cut, confirmation that FEMA-critical items remain to spec in Phase 1, vendor-provided Phase 2 pricing/timelines.

- NGO contact

- Action: Post draft conditional MOU to shared folder.

- Deliverable: MOU Draft v1 (includes amount, triggers, allowed uses limited to Phase 2 upgrades, timing, legal conditions) within 24 hours.

- Suggested essential terms (see Draft MOU section later).

- Procurement (Procurement & Legal)

- Action: Confirm phased-award evaluation criteria and required vendor documentation.

- Deliverable: Procurement Guidance Note v1 (12–24 hours).

- Provide advice on holdback/performance bond language and expedited waiver mechanics if necessary.

- Vendors

- Action: Submit two-option bids (Emergency Minimal + Standard) with upgrade pricing, lead-times, and FEMA-critical line-items explicitly marked.

- Timeline: Submit within 24 hours of RFQ issuance for rapid track.

- Lisa Carter (Analytics & Compliance)

- Action: Run rapid FEMA compliance pass within ~4 hours for rebids during working hours; prepare compliance memo flagging absolute non-negotiables and required QA evidence.

- Deliverable: Rapid Compliance Memo (for each rebid) within ~4 hours.

Sample short RFQ directive (to be inserted in RFQ amendment) - “Bidders must submit two structured offers: Offer A (Emergency Minimal / Phase 1) that strictly meets the FEMA_nonnegotiables checklist attached; Offer B (Standard / Phase 2) with optional upgrades. For Offer B, bidders must provide fixed upgrade unit prices and earliest completion date for upgrades. Any Offer A that omits FEMA_nonnegotiables items will be disqualified from Phase 1 award.”

## Implementation timeline and owners (detailed timeline and Gantt-like view)

High-level timeline (first two weeks) - T+0–12 hours - Oscar: Upload RFQ/SOW amendment; post thumbnails/BOM as available. - Marcos: Begin collecting and posting bidder clarifications. - T+12–36 hours - Vendors: Submit two-option bids. - Lisa: Rapid compliance pass on rebids (aim for ~4h turnaround during working hours). - NGO: Post draft conditional MOU. - Procurement: Confirm evaluation criteria and contract language. - T+36 hours–2 weeks - Conduct formal evaluation using evaluation matrix (see below). - Award Phase 1 to compliant vendor, finalize holdback/upgrade terms. - Begin ordering and logistics for Phase 1; execute QA acceptance tests and documentation collection for FEMA reimbursement.

Sample Gantt-style milestone table

| Milestone | Owner | Start | Target complete | Key outputs | |---|---:|---:|---:|---| | RFQ/SOW Amendment Issued | Oscar | T+0 | T+12h | RFQ Amendment v1 (doc) | | Vendor Clarifications Posted | Marcos | T+0 | T+12h | Clarifications Log | | Conditional MOU Draft | NGO contact | T+0 | T+24h | MOU v1 | | Two-option Bids Submitted | Vendors | T+12h | T+36h | Bid packages (A & B) | | Rapid Compliance Check | Lisa | upon each rebid | ~4h per rebid | Compliance memo | | Procurement finalizes evaluation & contract | Procurement | T+12h | T+24h | Evaluation matrix, contract template | | Evaluation & award recommendation | Wild Advice Partners / Procurement | T+36h | Day 7–14 | Award recommendation, procurement docs | | Phase 1 Order Placement | Procurement / Vendor | Day 7 | Day 14 | PO, schedule | | QA Acceptance & Documentation | Field QA / Vendor | As shipments arrive | Ongoing | QA reports, photos, invoices |

Owners & roles (expanded) - Analytics/Compliance: Lisa Carter — conducts compliance checks, creates compliance memos, supports analytics and mapping of vendor line-items to FEMA line-items. - RFQ & Design: Oscar — authors RFQ/SOW amendments, posts thumbnails and BOMs, coordinates with procurement for contract language. - Bid clarifications & Technical Q&A: Marcos — logs Q&A, synthesizes clarifications, posts consolidated addenda. - Procurement & Legal: Procurement team — finalizes contract template, holdback/performance bond language, evaluation criteria, and award mechanics. - Funding/Governance: NGO contact — drafts conditional MOU and provides bridge funding conditions. - Vendors / Supply: External bidders — provide two-option pricing, timelines, and QA proposals. - Wild Advice Partners: Lead evaluation, award recommendation, project planning for Phase 1 rollout and FEMA reimbursement support.

## Analysis plan (detailed)

- Compliance mapping (owner: Lisa)

- Deliverable: Line-item mapping spreadsheet (Vendor Item → FEMA Line-item → Compliant/Not Compliant → Required Evidence).

- Steps:

  - Ingest vendor BOM.

  - Map each vendor line-item to FEMA_nonnegotiables entries and FEMA line-item codes.

  - Flag items that are non-negotiable (hard fail) and conditional items (soft fail or acceptable with documented test results).

  - Output a compliance score (0–100) and a pass/fail result for Phase 1.

- Cost and schedule sensitivity (owner: Wild Advice Partners analytics team)

- Deliverable: Cost/Schedule Sensitivity Report.

- Steps:

  - Calculate cost delta between Phase 1 and Phase 2 at unit and program levels.

  - Model scenarios: immediate award to lowest compliant bidder; award to higher-price but faster vendor; award contingent on NGO funding.

  - Estimate the impact on funds required if upgrades are delayed or funded separately (include financing costs if short-term financing is used).

  - Provide a recommended procurement decision based on minimal combined expected cost to program and risk tolerance.

- QA & acceptance (owner: Field QA lead, Lisa for compliance)

- Deliverable: QA Acceptance Plan & Evidence Checklist.

- Steps:

  - Define acceptance tests per FEMA line-item (e.g., item count verification, material certificates, drop-test photos, anchoring installation photos).

  - Define evidence formats and storage locations (naming conventions, timestamped photos, geo-tagging if applicable).

  - Assign owners for evidence collection (vendor upon build, field QA upon receipt).

  - Define acceptance sign-off flow and retention policy for FEMA audit.

- Upgrade feasibility analysis (owner: Procurement + Wild Advice)

- Deliverable: Upgrade Feasibility Report.

- Steps:

  - Validate vendor upgrade timelines and capacity.

  - Model the lead time for Phase 2 upgrades and identify potential bottlenecks.

  - Create contingency plans for vendor non-performance.

## QA, acceptance criteria, and FEMA evidence requirements

Primary acceptance principles - For FEMA reimbursement, documentation is as important as the physical product. Acceptance must produce a clear, auditable trail linking ordered items to delivered items and payments.

Required artifacts (minimum) - Signed delivery acceptance certificate per PO line-item. - High-resolution photos of kits (front/inside/closeups of FEMA-critical items), dated and geo-tagged where possible. - Manufacturer certificates of conformity or test results for specified materials (e.g., tensile strength, flame resistance). - Packing list and commercial invoice matching PO line-items and unit counts. - Bill of materials (BOM) with serial numbers or batch numbers for traceable items. - QA test reports for structural items (e.g., anchoring/stowage tests) where required by FEMA_nonnegotiables. - Chain-of-custody documentation if kits are assembled in multiple locations.

Sample acceptance checklist (per delivery batch) - Delivery documentation: - [ ] Bill of lading received - [ ] Commercial invoice matches PO - [ ] Packing list counts verified - Physical verification: - [ ] Number of kits matches shipment - [ ] FEMA-critical items present and match spec - [ ] Anchoring/structural supports included and documented - Evidence captured: - [ ] Photos of each kit interior/exterior (3 angles) - [ ] Photos of any critical test or installation - [ ] Certificates attached for specified materials - QA signoff: - [ ] Vendor internal QA release form - [ ] Field QA acceptance with signature and timestamp - [ ] Upload of all evidence to shared folder with naming conventions

Evidence naming convention (example) - {VendorShort}{PO#}{Batch#}{Date YYYYMMDD}{KitSeq#}_{DocType}.{ext} - Example: ACME_PO1234_B01_20260201_KIT001_PHOTO1.jpg

Retention and audit - All acceptance evidence must be stored in the shared folder and indexed in the compliance mapping spreadsheet. Maintain for at least the FEMA-required period (confirm with agency; typically multi-year). Provide a single packaged audit file per batch for reimbursement submissions.

## Detailed RFQ/SOW amendment guidance (templates and mandatory language)

Key RFQ amendment sections (to include) 1. Introduction & Purpose 2. Submission requirements 3. Two-option bid structure and mandatory content 4. FEMA_nonnegotiables attachment (mandatory compliance baseline) 5. Evaluation criteria and scoring 6. Contractual terms: holdback, upgrade option, warranties, remedies 7. Acceptance & QA evidence required 8. Timeline and delivery milestones 9. Questions & clarifications process 10. Attachments: FEMA_nonnegotiables_Lisa.pdf, sample acceptance certificate, evidence naming convention

Sample RFQ language snippets (editable) - Two-option bid requirement: - “Bidders shall submit two separate and clearly labeled offers: - Offer A: Emergency Minimal / Phase 1 (Mandatory FEMA compliance). Must include BOM mapped to FEMA_nonnegotiables. - Offer B: Standard / Phase 2 (Optional upgrades). Must include fixed upgrade unit pricing and earliest feasible completion date. - Bidders must include a combined summary table showing delta costs and delta lead-times between Offer A and Offer B.” - Mandatory compliance: - “Offer A must fully comply with the FEMA_nonnegotiables checklist. Any omission in Offer A of a FEMA non-negotiable item will lead to disqualification for Phase 1 award.” - Upgrade option clause (contract preview): - “The Purchase Order shall include an Upgrade Option allowing the Buyer to order additional components or upgrades in accordance with Offer B at the fixed prices specified. The Seller guarantees availability of upgrades at the prices and lead-times stated in the bid for a minimum of 120 days from the date of offer submission.”

Suggested holdback clause (procurement-ready language) - “The Buyer shall withhold [15–30]% of the Phase 1 contract value until final acceptance of Phase 1 deliverables and, where applicable, either: (a) completion and acceptance of Phase 2 upgrades; or (b) submission of NGO funding confirmation for Phase 2 or approved alternate remedy. Liquidated damages for failure to complete upgrades shall be limited to the withheld portion or a pre-agreed amount.”

Suggested performance bond clause - “The Seller shall provide a performance bond equal to [10–20]% of Phase 1 PO value, or a bank guarantee acceptable to the Buyer, to secure fulfillment of contract obligations including upgrade options. The bond may be drawn upon if the Seller fails to deliver conforming upgrades per contract terms.”

## Evaluation matrix and scorecard (sample)

Use as both procurement evaluation tool and decision aid.

Sample evaluation matrix (weights are illustrative — adjust per procurement policy)

| Criterion | Weight (%) | Minimum pass? | Scoring notes | |---|---:|:---:|---| | FEMA Non-negotiables compliance (Offer A) | 30 | Yes (must pass) | Binary: Pass/Fail. Fail = disqualified for Phase 1. | | Price (Phase 1) | 20 | No | Score inverse to price; lowest gets full points. | | Upgrade fixed pricing & timeline (Offer B) | 15 | No | Score based on competitiveness and clarity of upgrade path. | | Lead time (Phase 1 delivery) | 10 | No | Faster lead times score higher. | | QA plan and evidence readiness | 10 | No | Presence of acceptance tests, evidence plan, certificates. | | Vendor capacity & past performance | 10 | No | References, production capacity, contingency plans. | | Warranty & remedies | 5 | No | Warranty period, replacement terms, responsiveness. | | TOTAL | 100 | — | — |

Example scoring methodology - For price: Score = (Lowest Price / Vendor Price) * Weight - For lead time: Score scaled similarly to a minimum acceptable threshold. - For upgrade pricing: award full points only if fixed in bid and tied to a firm timeline.

Award recommendation decision rule - All bidders must pass the FEMA non-negotiables check for Offer A to be considered for Phase 1. - Select the bidder with the highest total weighted score among passing bidders. - If no bidder passes FEMA non-negotiables, consider emergency procurement exemptions or extend RFQ timeline to allow remedy.

## Risk register (detailed)

Comprehensive risk table with likelihood, impact, and mitigations.

| Risk | Likelihood (H/M/L) | Impact (H/M/L) | Primary owner | Mitigations | |---|---:|---:|---|---| | NGO bridge funding delayed or restrictive | M | H | NGO contact / Project lead | Proceed with Phase 1 award using contingency finance; include contractual holdback for Phase 2; seek short-term financing or staged payments; escalate to governance. | | Vendors omit FEMA-critical items to reduce price | M | H | Procurement / Oscar | Require FEMA_nonnegotiables as mandatory; disqualify non-compliant bids; run rapid compliance checks; include pre-award verification. | | Procurement legal constraints on phased-award mechanics | M | M | Procurement | Pre-clear contract language; propose use of holdback/performance-bond; prepare waiver paths and escalation to legal counsel. | | Vendor inability to meet upgrade timelines | M | M | Procurement / Vendor | Require fixed upgrade pricing and committed timeline in bid; include remedies and penalties; have alternate vendors pre-qualified. | | QA evidence incomplete or insufficient for FEMA | L/M | H | Field QA / Lisa | Provide explicit evidence templates in RFQ; require evidence for acceptance; assign field QA to verify upon delivery; maintain audit package. | | Supply chain delays for critical components | M | M | Vendor / Procurement | Request vendor capacity statements; require alternate sources; include schedule buffers; consider partial shipments. | | Price increases post-award due to currency or material costs | M | M | Procurement | Fix prices for Phase 1 in contract; for upgrades, require fixed pricing for a minimum period; include supplier price escalation clauses only with strict caps. | | Multiple vendors failing compliance, need to re-open competition | L/M | H | Wild Advice Partners / Procurement | Prepare contingency procurement path; allow emergency procurement; increase vendor outreach. |

For each risk, define triggers for escalation (e.g., vendor missing 48-hour milestone, NGO failing to post MOU within 72 hours) and a person responsible for triggering mitigations.

## Deliverables (detailed table with owners, required formats, and deadlines)

| Deliverable | Owner | Format | Deadline | Purpose/Notes | |---|---:|---:|---:|---| | RFQ/SOW amendment v1 | Oscar | DOCX/PDF | T+12h | Basis for two-option bids | | Clarifications log v1 | Marcos | Spreadsheet + PDF | T+12h | Consolidated vendor Q&A | | Conditional MOU draft v1 | NGO contact | PDF | T+24h | Bridge funding terms | | Procurement guidance & contract template | Procurement | DOCX/PDF | T+24h | Holdback/performance-bond language | | Two-option bids | Vendors | PDF + BOM spreadsheet | T+24–36h | Evaluation input | | Rapid FEMA compliance memo (per rebid) | Lisa | PDF | ~4h after each rebid | Compliance pass/fail and notes | | Evaluation matrix populated | Wild Advice Partners / Procurement | Spreadsheet | T+36h–Day 7 | Comparative scoring | | Award recommendation | Wild Advice Partners | Memo | Day 7–14 | Recommend Phase 1 award | | Phase 1 project plan | Wild Advice Partners | DOCX + Gantt | Post-award | Logistics and QA plan | | QA acceptance reports (per batch) | Field QA / Vendor | PDF + photos | Ongoing | For FEMA reimbursement | | Audit package for FEMA | Wild Advice Partners | ZIP (docs) | Post-delivery | Full evidence bundle |

Status tracking: maintain a master tracker in the shared folder with document links, owners, and real-time status updates.

## Budget & funding considerations

High-level financial mechanics - Phase 1 cost should be evaluated both as standalone and as a component of a combined Phase 1+2 program cost. - NGO conditional MOU should specify whether funds are contingent on: - Proof of Phase 1 delivery and acceptance. - Vendor-provided upgrade pricing being fixed and acceptable. - A specific timeline for disbursement to enable upgrade completion.

Suggested financial guardrails - Holdback percentage: 15%–30% of Phase 1 payment retained pending either upgrade completion or NGO confirmation of funding. - If NGO provides bridge funding, require that funds be held in escrow or released on completion milestones to reduce counterparty risk. - Consider short-term financing or invoice factoring for vendor cashflow to accelerate delivery if vendor requires up-front capital — only where program risk is acceptably low and contractually secured.

Cost sensitivity example (illustrative) - Phase 1 unit cost (Offer A): $100 per kit - Phase 2 upgrade cost (delta): $25 per kit - Holdback @ 20% per kit: $20 per kit withheld until Phase 2 acceptance or funding confirmation. - If NGO bridge funding delayed 30 days, vendor may require faster payment terms — consider using a 30% performance bond instead of cash holdback if vendor cashflow is a concern.

## Communication plan

Stakeholders and communication responsibilities - Internal project updates (daily during immediate period): Oscar to email progress updates to distribution list; include stand-up notes, action items, and link to shared folder. - Vendor communications: Marcos to manage bidder Q&A and issue clarifications publicly to maintain fairness. - Funding communications: NGO contact to post MOU draft and communicate funding triggers and timelines directly to Procurement and Wild Advice Partners. - Compliance communications: Lisa to notify Procurement of any immediate compliance red flags and produce memos attached to bid packages. - Executive escalation: Wild Advice Partners to escalate to executive sponsors if funding or procurement constraints jeopardize timely award.

Suggested cadence - T+24h: Joint sync call (10:30 local) — review inputs, outstanding clarifications, compliance findings, and obtain consensus for recommendation. - Daily stand-up (short, 15–20 minutes) during the 0–72 hour window: Oscar (RFQ), Marcos (clarifications), Lisa (compliance), Procurement, NGO rep. - Weekly steering update for sponsors until Phase 2 funding fully secured.

Email template for urgent RFQ update (example) - Subject: Urgent: RFQ Amendment Published – Action Required (Phase 1 FEMA Mapping) - Body: Brief summary, required action, deadlines, link to folder, contact for questions.

## Contract templates and sample clauses (detailed examples)

- FEMA compliance representation and warranty

- “Seller represents and warrants that Offer A (Emergency Minimal) fully complies with the FEMA_nonnegotiables checklist attached as Appendix A to this Purchase Order. Seller must provide, at delivery, all documentation and evidence described in Section X of this SOW sufficient for Buyer to pursue FEMA reimbursement. Any failure to deliver compliant goods entitles Buyer to remedies including withholding payment, return at Seller expense, or contract termination.”

- Upgrade option and pricing guarantee

- “Seller guarantees that Upgrade Option pricing (Offer B) shall remain fixed and available for ordering by Buyer for a period of 120 days from bid submission. Should Buyer exercise the Upgrade Option, Seller shall deliver upgraded kits within the timeline specified in Offer B. Failure to meet upgrade timelines shall invoke contract remedies as described in Section Y.”

- Holdback and performance bond

- Holdback clause (see RFQ section).

- Sample performance bond language provided earlier; procurement to select preferred instrument (bond vs. escrow vs. letter of credit).

- Acceptance and evidence clause

- “Acceptance of Phase 1 shipments requires: (a) inspection; (b) receipt of evidence files (photos, certificates, invoices) uploaded to Buyer’s shared folder; (c) execution of acceptance certificate. Buyer will release invoice payment per milestones, with the final holdback released upon satisfaction of acceptance evidence and, if applicable, completion of upgrade milestones.”

- Remedies

- “If Seller fails to deliver compliant Phase 1 or to perform upgrade options per contract, Buyer may pursue remedy including: withholding of holdback; engaging alternate supplier at Seller expense, up to withheld amount; claim against performance bond.”

Legal note: Procurement/legal should adapt clauses to organizational procurement rules and local law. Above is sample language for quick use in drafting.

## FEMA reimbursement submission checklist (operationalized)

To be prepared for FEMA audit and reimbursement, collect and prepare the following for each delivery batch:

- Contract / Purchase Order copies.

- Signed acceptance certificates (vendor, buyer).

- Commercial invoices and packing lists matching shipment.

- Photos (dated & geo-tagged): kit exterior, kit interior, close-up of FEMA-critical items.

- Manufacturer certificates and test reports for specified items.

- QA test results (e.g., anchoring test, load test).

- Delivery receipts / proof of shipment.

- NGO funding documents (if used for Phase 2).

- Bank payment records matching invoice.

- Consolidated audit package (single ZIP file named per naming convention) stored in shared folder.

Prepare a FEMA submission memo summarizing compliance and attesting to the authenticity of evidence, with a sign-off from authorized program lead.

## Next steps (priority sequence with clarifications and timings)

Priority list (immediate) 1. Oscar: Upload RFQ/SOW amendment and CC team (T+12h). Include mandatory FEMA checklist and sample contract language. 2. Marcos: Post bidder clarifications (T+12h). Consolidate Q&A and update RFQ if needed. 3. NGO: Post conditional MOU draft (T+24h). Ensure MOU clearly ties funding to Phase 2 upgrades and sets release triggers. 4. Procurement: Confirm phased-award mechanics and holdback language (T+24h). Provide final evaluation matrix and legal vetting. 5. Vendors: Submit two-option bids (T+24–36h). Ensure Offer A maps to FEMA_nonnegotiables and Offer B lists fixed upgrade prices. 6. Lisa: Rapid compliance pass on rebids (4h turnaround during working hours). Produce compliance memos for each bidder. 7. T+24 sync: Review inputs and agree on award recommendation (10:30 local).

Follow-on steps (post-award) - Finalize contract signing with holdback and upgrade clauses. - Execute purchase order and schedule shipments. - Deploy field QA to receive and verify first shipments. - Prepare FEMA submission package per checklist. - Initiate upgrade order (Phase 2) upon NGO fund confirmation or contract-triggered milestone.

## Appendix A — FEMA_nonnegotiables_Lisa.pdf (summary and usage guidance)

Note: The actual one-page FEMA_nonnegotiables_Lisa.pdf is attached to the RFQ. Below is a summarized usage guidance for reviewers and vendors.

Key non-negotiables (examples; please refer to attached one-page for exact requirements) - Anchoring/structural supports must be present for items requiring secure installation. - Materials must meet specified technical standards (e.g., flame retardancy, tensile strength). - Certain items (e.g., shelter components, specific medical supplies) must match FEMA line-item codes and unit counts exactly. - QA evidence including manufacturer certificates and acceptance photos must accompany deliveries.

Vendor mapping requirement - For every line-item in Offer A, vendors must: - Provide a direct map to the FEMA line-item code. - Supply evidence type (photo, test certificate) to be delivered with shipment. - Indicate manufacturer and batch/serial number where applicable.

Evaluator checklist - Use the FEMA_nonnegotiables checklist as the first evaluation gate. Mark PASS/FAIL per vendor. Only PASS vendors proceed to weighted scoring.

## Appendix B — Sample documents (skeletons)

- Sample conditional MOU (skeleton)

- Parties: NGO (name) and Buyer (name)

- Purpose: Conditional funds to support Phase 2 upgrades

- Amount: $X (maximum)

- Triggers: [e.g., Buyer provides evidence of Phase 1 acceptance per Appendix B]

- Use restrictions: Funds limited to Phase 2 upgrade payment(s)

- Timing: Funds to be disbursed within Y days of trigger

- Legal: Confidentiality, liability, termination clauses

- Signatories: Authorized NGO official; Buyer representative

- Sample Compliance Memo (template)

- Vendor:

- Bid received:

- Offer A compliance summary:

- FEMA_nonnegotiables: PASS/FAIL with notes

- Required evidence missing: list

- Recommended holdbacks or pre-conditions: list

- Recommendation: Proceed / Clarify / Disqualify

- Signed: Lisa Carter

- Sample Evaluation Scorecard (spreadsheet fields)

- Vendor name; Offer ID; Price Phase1; Price Phase2; Lead time Phase1; Time Phase2; Compliance pass/fail; QA readiness; Total score; Recommendation.

Prepared by: Lisa Carter Data Scientist, Wild Advice Partners

For questions or clarifications, please CC me on uploads to the shared folder (link here) — I will prioritize a rapid compliance pass upon receipt.